## conl ldgr1
Jagriti Child and Youth Concern
Kathmandu, Nepal
CONTROL LEDGER (CASH & BANK) SHEET
Date | Particulars | VR# | Code Construction | Janta Bank |  | Cash | Advance | Expenses | [8 empty] | Receivable | Payable | Fund
|  |  |  | Cheque No. | Amount NPR |  |  | Construction | Monitoring & Evaluation | Awareness Campaing | SWC Monitoring | Inaguration & Handover | Human Resource
[13 empty] | Coordinator | AFO | Social Mobilzier | Rent/Utility
2018-11-14 | Refreshment A/C | 1 | [13 empty] | 1667 |  | 1667
2018-12-07 | Fund received A/C | 2 |  |  | 2831890 | [13 empty] | 2831890
2018-12-07 | Bank Charge A/C | 3 |  |  | -200 | [10 empty] | 200
2018-12-10 | Shraddha Verma A/C | 4 |  | 8244433 | -40000 |  | 40000
2019-12-20 | Shraddha Verma A/C | 5 |  | 8244434 | -2520 |  | -40000 |  | 42520
2018-12-20 | Travel A/C | 6 |  | 8244435 | -25967 |  |  |  | 27000 | [8 empty] | 1033
2018-12-21 | Shree Gorakhikalika A/C | 7 |  | 8244438 | -1175000 |  | 1175000
2019-01-03 | Jagriti Child and Youth Concern Nepal | 8 |  | 8244439 | -552612 | [11 empty] | 552612
2019-01-10 | Jagriti Child and Youth Concern Nepal | 9 |  | 8244441 | -225000 | [11 empty] | 225000
2019-01-10 | Nov-Dec Salary A/C | 10 |  | 8244442,43,44 | -178200 | [7 empty] | 120000 | 30000 | 30000 |  |  | 1800
2019-01-22 | Travel A/C | 11 |  | 8244447 | -40500 |  |  |  | 45000 | [8 empty] | 4500
2019-01-22 | Tax paid A/C | 12 |  | 8244446 | -9000 | [12 empty] | -9000
2019-01-23 | Jagriti Child and Youth Concern Nepal | 13 |  |  | 225000 | [11 empty] | -225000
2019-01-23 | Jagriti Child and Youth Concern Nepal | 14 |  |  | 552612 | [11 empty] | -552612
2019-01-29 | Jan Salary A/C | 15 |  | 8244448,49,50 | -87900 | [7 empty] | 60000 | 15000 | 15000 |  |  | 2100
2019-01-30 | Office Rent A/C | 16 |  | 8244452 | -10000 | [10 empty] | 10000
2019-01-30 | Banner Exp A/C | 17 | [13 empty] | 904 |  | 904
2019-01-30 | Travel A/C | 18 |  | 8244453 | -13500 |  |  |  | 15000 | [8 empty] | 1500
2019-01-30 | DSA A/C | 19 |  | 8244454,55 | -12000 |  |  |  | 12000
2019-02-19 | Tilottam Paudel A/C | 20 |  | 8244456 | -50000 |  | 50000
2019-02-27 | Feb Salary A/C | 21 |  | 8244457,58,59 | -87900 | [7 empty] | 60000 | 15000 | 15000 |  |  | 2100
2019-02-27 | Office Rent A/C | 22 |  | 8244460 | -10000 | [10 empty] | 10000
2019-02-27 | E/W in Excavation | 23 | 1.1 |  |  |  |  | 169235.98
2019-02-27 | Stone Soling with Sand | 23 | 1.2 |  |  |  |  | 136180.96
2019-02-27 | S/M Work in 1:6 c/s mortar | 23 | 1.3 |  |  |  |  | 462598.49
2019-02-27 | PCC (1:3:6) | 23 | 1.4 |  |  |  |  | 64098.97
2019-02-27 | R.C.C Work in 1:1.5:3 | 23 | 1.5 |  |  |  |  | 653034.13
2019-02-27 | Reinforcement for RCC Works (as per Bar Schedule) | 23 | 1.6 |  |  |  |  | 387570.87
2019-02-27 | FormWork | 23 | 1.8 |  |  |  |  | 80424.38
2019-02-27 | User commity management Cost | 23 | 1.18 |  |  |  |  | 39062.88
2019-02-27 | Contingency Charge | 23 | 1.19 |  |  |  |  | 58594.31
2019-02-27 | Soil test | 23 | 1.2 |  |  |  |  | 350000
2019-02-27 | Shree Gorakhikalika A/C | 23 |  |  |  |  | -1175000 | [10 empty] | 1225800.97
2019-02-27 | Banner Exp A/C | 24 |  | 8244461 | -1808 |  |  |  |  | 904 | [7 empty] | -904
2019-03-05 | Travel A/C | 25 |  | 8244462 | -81000 |  |  |  | 45000 | [7 empty] | 40500 | 4500
2019-03-07 | Deepak Prasad Bashyal | 26 |  | 7491142 | -349200 |  | 349200
2019-03-21 | Fund received A/C | 27 |  |  | 1032669 | [13 empty] | 1032669
2019-03-25 | Shree Gorakhikalika A/C | 28 |  | 7491143 | -1175000 | [12 empty] | -1175000
2019-03-27 | Mar Salary A/C | 29 |  | 7491144,45 | -29700 |  | -58200 | [5 empty] | 60000 | 15000 | 15000 |  |  | 2100
2019-03-27 | Office Rent A/C | 30 |  | 7491146 | -10000 | [10 empty] | 10000
2019-03-27 | DSA & Refreshment A/C | 31 |  |  | 27875 |  | -50000 |  |  | 22125
2019-03-27 | Fund received A/C | 32 |  |  | 1038400 | [13 empty] | 1038400
2019-03-31 | Bank Charge A/C | 33 |  |  | -200 | [10 empty] | 200
2019-03-31 | Tax paid A/C | 34 |  | 7491147 | -12300 | [12 empty] | -12300
| Total Expenses this month |  |  |  | 1528939 | 0 | 291000 | 2400800.97 | 186520 | 23029 | 0 | 0 | 300000 | 75000 | 75000 | 32971 | 40500 | 50800.97 | 4902959
Total Expenses upto March 2019
| Total |  |  |  | 1528939 | 0 | 291000 | 2400800.97 | 186520 | 23029 | 0 | 0 | 300000 | 75000 | 75000 | 32971 | 40500 | 50800.97 | 4902959
[16 empty] | 257.868 |  | 397.3171
3093320.97
Prepared By: | [16 empty] | Approved By
Signature: | [16 empty] | Signature:
Name: Amrit Kumar Lamichhane | [16 empty] | Name: Tilottam Paudel
Designation: Admin and Finance Officer | [16 empty] | Designation: President
Date: 26 April 2019 | [16 empty] | Date: 26 April 2019

## Detials of Construction Expense
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
S.N | Particulars | Unit | Qty | Unit Cost | Days/Month | Times/Event | Total Amount in NPR | Total Amount in USD | Nov Expenses | Dec Expenses | Jan Expenses | Feb Expenses | March Expenses | April Expenses | May Expenses | June Expenses | July Expenses | Aug Expenses | Sept Expenses | Oct Expenses | Total Expenses | Budget Balance | Spent % | Remarks for fund request and Variance
1 | Construction | 4700000 |  |  |  |  | 4700000 | 42727.2727 |  |  |  | 2400800.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400800.97 |  | 51.08%
1.1 | E/W in Excavation | [10 empty] | 169235.98
1.2 | Stone Soling with Sand | [10 empty] | 136180.96
1.3 | S/M Work in 1:6 c/s mortar | [10 empty] | 462598.49
1.4 | PCC (1:3:6) | [10 empty] | 64098.97
1.5 | R.C.C Work in 1:1.5:3 | [10 empty] | 653034.13
1.6 | Reinforcement for RCC Works (as per Bar Schedule) | [10 empty] | 387570.87
1.7 | B/W Works in 1:6 C/S Mortar | [10 empty] | 0
1.8 | FormWork | [10 empty] | 80424.38
1.9 | Supply, making & fixing of Door & window using Ms Angle, plates & other accessories with painting | [10 empty] | 0
1.10 | 12.5 mm Thick Plaster in 1:4 C/S Mortar | [10 empty] | 0
1.11 | Earth Filling | [10 empty] | 0
1.12 | 20 mm Thick Plaster in 1:4 C/S Mortar | [10 empty] | 0
1.13 | Punning | [10 empty] | 0
1.14 | Two Coat Snowcem Painting Works | [10 empty] | 0
1.15 | SAl Wood for Parlin & Rafter | [10 empty] | 0
1.16 | CGI Roofing By 26 Gauge Colour Sheet | [10 empty] | 0
1.17 | Electrification | [10 empty] | 0
1.18 | User commity management Cost @2 % | [10 empty] | 39062.88
1.19 | Contingency Charge @3 % | [10 empty] | 58594.31
1.20 | Soil test | [10 empty] | 350000
| Construction Total Cost | [5 empty] | 4700000 | 42727.2727 | 0 | 0 | 0 | 2400800.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400800.97 | 0 | 51.08%
| Prepared By | [19 empty] | Approved By
| Signature: | [19 empty] | Signature:
| Name: Amrit Kumar Lamichhane | [19 empty] | Name: Tilottam Paudel
| Designation: Admin and Finance Officer | [19 empty] | Designation: President
| Date: 26 April 2019 | [19 empty] | Date: 26 April 2019

## Bug vs Exp
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
S.N | Particulars | Unit | Qty | Unit Cost | Days/Month | Times/Event | Total Amount in NPR | Total Amount in USD | Nov Expenses | Dec Expenses | Jan Expenses | Feb Expenses | March Expenses | April Expenses | May Expenses | June Expenses | July Expenses | Aug Expenses | Sept Expenses | Oct Expenses | Total Expenses | Budget Balance | Spent % | Remarks for fund request and Variance
A | Program Cost | [5 empty] | 5625000 | 51136.3636 | 0 | 69520 | 72000 | 2401704.97 | 67125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2610349.97 | 3014650.03 | 46.41%
1 | Construction | 4700000 |  |  |  |  | 4700000 | 42727.2727 |  |  |  | 2400800.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400800.97 | 2299199.03 | 51.08%
2 | Monitoring/Evaluation/Reporting | 550000 |  |  |  |  | 550000 | 5000 |  | 69520 | 72000 | 0 | 45000 | [7 empty] | 186520 | 363480 | 33.91%
3 | Awareness Campaing on School Safety and Child Friendly Local Governance to Community and School | 75000 |  |  |  |  | 75000 | 681.8182 |  |  |  | 904 | 22125 | [7 empty] | 23029 | 51971 | 30.71%
4 | SWC Monitoring | 100000 |  |  |  |  | 100000 | 909.0909 | [12 empty] | 0 | 100000 | 0%
5 | Inaguration and handover Ceremony | 200000 |  |  |  |  | 200000 | 1818.1818 | [12 empty] | 0 | 200000 | 0%
| HR/Admin | [5 empty] | 1316000 | 11963.6364 | 1667 | 200 | 280904 | 100000 | 100200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482971 | 833029 | 36.7%
6 | Coordinator | [5 empty] | 780000 | 7090.9091 |  |  | 180000 | 60000 | 60000 | [7 empty] | 300000 | 480000 | 38.46%
7 | Admin/Finance Assistant | [5 empty] | 195000 | 1772.7273 |  |  | 45000 | 15000 | 15000 | [7 empty] | 75000 | 120000 | 38.46%
8 | Social Mobilizer | [5 empty] | 195000 | 1772.7273 |  |  | 45000 | 15000 | 15000 | [7 empty] | 75000 | 120000 | 38.46%
9 | Office Rent/Utilities/Equipment/Stationary/Maintenance/Preparation meetings/Refreshment | [5 empty] | 146000 | 1327.2727 | 1667 | 200 | 10904 | 10000 | 10200 | [7 empty] | 32971 | 113029 | 22.58%
| Grand Total | [5 empty] | 6941000 | 63100 | 1667 | 69720 | 352904 | 2501704.97 | 167325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3093320.97 | 3847679.03 | 44.57%
| Prepared By | [19 empty] | Approved By
| Signature: | [19 empty] | Signature:
| Name: Amrit Kumar Lamichhane | [19 empty] | Name: Tilottam Paudel
| Designation: Admin and Finance Officer | [19 empty] | Designation: President
| Date: 26 April 2019 | [19 empty] | Date: 26 April 2019

## Advance Sheet
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
Advance Sheet
S.N | Particular | Voucher No | Tilottam Poudel | Deepak P Bashyal | Amount
1 | Advance for Monitoring and Awerness Program | 20 | 50000 |  | 50000
2 | Salary Advance as per JCYCN Policy | 26 |  | 349200 | 349200
3 | Less March Advance Salary | 29 |  | -58200 | -58200
4 | Advance Adjustment(Monitoring and Awerness Program) | 31 | -50000 |  | -50000
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
27 |  |  |  |  | 0
| Total |  | 0 | 291000 | 291000
| Prepared By |  |  | Approved By
| Signature: |  |  | Signature:
| Name: Amrit Kumar Lamichhane |  |  | Name: Tilottam Paudel
| Designation: Admin and Finance Officer |  |  | Designation: President
| Date: 26 April 2019 |  |  | Date: 26 April 2019

## Payable & Receviable Sheet
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
Payable Sheet
S.N | Date | Date | Particulars | Voucher .No | Amount | Purpose
1 | 2019-03-01 |  | Gorakh kalika Sec School |  | 1231500.97 | Construction expenses booked on payable
2 | 2019-03-05 |  | Vehicle Hire Tax Payable | 25 | 4500 | Vehicle Hiring Tax payable
3 | 2019-03-25 |  | Gorakh kalika Sec School | 27 | -1175000 | First Installment advance settled of Construction
4 | 2019-03-27 |  | SST Payable | 29 | 2100 | March Salary SST Payable
5 | 2019-03-31 |  | Rental tax Paid | 37 | -6000 | Vehicle Hiring Tax paid
6 | 2019-03-31 |  | SSt Paid | 37 | -6300 | Salary tax paid
7
8
9
10
11
12
13
14
15
16
17
18
19
Total |  |  |  |  | 50800.97
Receviable Sheet
S.N | Date | Particulars |  | Voucher. No | Amount | Purpose
1 | 2019-03-05 | Receviable From JCYCN |  | 25 | 40500 | Monitoring Travel expenses receivable from Jagriti Child and youth Concern Nepal
2
3
4
5
6
7
8
9
10
11
12
Total |  |  |  |  | 40500
Prepared By |  |  |  |  | Approved By
Signature: |  |  |  |  | Signature:
Name: Amrit Kumar Lamichhane |  |  |  |  | Name: Tilottam Paudel
Designation: Admin and Finance Officer |  |  |  |  | Designation: President
Date: 26 April 2019 |  |  |  |  | Date: 26 April 2019

## Trial Balance
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
Trail Balance
S.N | PARTICULAR | L.F | DR.AMOUNT | CR. AMOUNT
1 | Opening Bank Balance |  |  | 0
1.2 | Fund Received |  |  | 4902959
1.3 | Advance |  | 291000
1.4 | Cash |  | 0
1.5 | Receivable |  | 40500
1.6 | Bank balance |  | 1528939
| SUB-TOAL(A) |  | 1860439 | 4902959
| Payables |  |  | 50800.97
2 | Program Activities
1 | Construction |  | 2400800.97
2 | Monitoring/Evaluation/Reporting |  | 186520
3 | Awareness Campaing on School Safety and Child Friendly Local Governance to Community and School |  | 23029
4 | SWC Monitoring |  | 0
5 | Inaguration and handover Ceremony |  | 0
6 | Coordinator |  | 300000
7 | Admin/Finance Assistant |  | 75000
8 | Social Mobilizer |  | 75000
9 | Office Rent/Utilities/Equipment/Stationary/Maintenance/Preparation meetings/Refreshment |  | 32971
| SUB-TOAL (B) |  | 3093320.97 | 50800.97
| TOTAL PROGRAMME BUDGET (A+B) |  | 4953759.97 | 4953759.97
Prepared By |  |  |  | Approved By
Signature: |  |  |  | Signature:
Name: Amrit Kumar Lamichhane |  |  |  | Name: Tilottam Paudel
Designation: Admin and Finance Officer |  |  |  | Designation: President
Date: 26 April 2019 |  |  |  | Date: 26 April 2019
0

## BRS
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
Bank Reconciliation Statement
Name of Bank: | Janata Bank
Account Title: | Jagriti Child and Youth Concern Nepal (KANALLAN)
Account No: | 037002046864205
Date | Descriptions | [5 empty] | Amount (Rs.)
2019-02-28 | Balance as per Ledger Book | [5 empty] | 1528939
Add: | Outstanding Cheques
| S.No. | Payee | Cheque No: | Date | Vr.no | Amount
| 1 | Sabita Pangani | 7491145 | 2019-03-27 | 29 | 14850
| 2 | Deepak Sharma | 7491147 | 2019-03-31 | 37 | 12300
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
27150
Add:
| 1 | Other Fund |  |  |  |  | 5292.96
| 2 | Jagriti Child and Youth Concern Nepal Fund |  |  |  | 5292.96
32442.96
Add: | [6 empty] | 1561381.96
1
2
Less: | Bank Charges
1
2
Less: | Deposit in transit
| 1 | Tilottam Paudel |  | 2019-03-27 | 31 | 27875
27875
| Balance as per bank statement as on 31 mar 2019 | [5 empty] | 1533506.96
Prepared By: | [5 empty] | Approved By:
Signature: | [5 empty] | Signature:
Name: Amrit Kumar Lamichhane | [5 empty] | Name: Tilottam Paudel
Designation: Admin and Finance Officer | [5 empty] | Designation: President
Date: 26 April 2019 | [5 empty] | Date: 26 April 2019

## FAS
Implementing Partner: Jagriti Child and Youth Concern Nepal
Support: KANALLAN
Project Name: School Building Construction |  |  |  | pau
Project Period: Nov 2018-Oct 2019
Reporting Month: March 2019
Fund Accountability Statement
| Particulars |  | Amount (Rs.)
A. | Opening Fund Balance
| Bank | Opening Bank Balance
Receivables
| Sub-total |  | 0
B. | Add: | Fund Received
|  | 1st installment received | 2831890
|  | 2nd installment received | 2071069
3rd installment received
4th installment received
Interest from Bank
Other income
| Sub-total |  | 4902959
C. | Total Available Fund (A+B) |  | 4902959
D. | Less: | Expenditure
|  | Expenses of Nov 18 | 1667
|  | Expenses of Dec 18 | 69720
|  | Expenses of Jan 19 | 352904
|  | Expenses of Feb | 2501704.97
|  | Expenses of March | 167325
|  | Expenses of April | 0
|  | Expenses of May | 0
|  | Expenses of June | 0
|  | Expenses of July | 0
|  | Expenses of August | 0
|  | Expenses of Sept | 0
|  | Expenses of Oct | 0
| Sub-total |  | 3093320.97
E. | Closing Fund Balance (C-D) |  | 1809638.03
F. | Closing Fund Balance Represented by:
| Cash |  | 0
| Bank |  | 1528939
|  | Advance | 291000
| Payables |  | -50800.97
| Receivable | Receivable | 40500
Net Fund Balance |  |  | 1809638.03
0
Prepared By |  |  | Approved By
Signature: |  |  | Signature:
Name: Amrit Kumar Lamichhane |  |  | Name: Tilottam Paudel
Designation: Admin and Finance Officer |  |  | Designation: President
Date: 26 April 2019 |  |  | Date: 26 April 2019